Ministry of Education and Training 	Catholic Relief Services – Vietnam

The project “Enhancing access and quality of inclusive education
through information technology for children with disabilities”

Based on project approval Decision No.1937/QĐ-BGD-ĐT

TERMS OF REFERENCE

NATIONAL CONSULTANTS TO DEVELOP E-LEARNING LESSONS

FOR INFORMATION TECHNOLOGY AND PHILOLOGY OF GRADE 6 FOR CHILDREN WITH HEARING AND VISUAL IMPAIREMENTS

- Project back ground

In the framework of the project "Enhancing access and quality of education through ICT integration for children with disabilities" of the Ministry of Education and Training (MOET) approved by Decision No. 1937/QĐ-BGDĐT with the cooperation of Catholic Relief Services (CRS), and United States  Agency for International Development  (USAID), CRS and MOET have  been implemeting and piloting distance learning education for children with disabilities, who do not have the access to go to school through ICT application (enclosed a model draft). The development and pilot model to develop and test a number of technology solutions, implementing measures to reduce barriers for CwD to access to quality education.

In May, 2013 an international expert came and work with the project board of management, CRS and local experts to develop a model of distance education, that’s suitable with Vietnam. The International expert provided a proposed model of distance education, and recommendations to fit the context of Vietnam. The International expert proposed a model for distance education and some recommendations.

Project in collaboration with local experts and local areas to indentify children with visual, and hearing impairments, who have completed primary school but did not continue lower secondary school, to do a needs survey/assesssment of children in Thai Nguyen, Ha Noi and Hai Phong. Up to now, the specialists have indentified more than 30 children with disabilities who have met the criteria for project participation. There maybe some more children with visual impairment eligible to participate, these children are residing in Hai Phong. Beside that the project is planning to extend using of the e-learning website towards CwD at special schools and center for education of CwD. The project will pilot extend the distance learning for hearing and seeing impairment children in grade 6 with two subjects IT and philology.

During the time from September 2012 to February 2014, a group of consultants have been developing e-learning lessons with duration of 25 lessons for hearing impaired children, 25 lessons for visual impaired children; 30 lessons of philology for visual impaired children, and 30 lessons of philology for hearing impaired children. All the aboved lessons have been approved and uploaded to the distance learning website, to be ready for the pilot period. All the lessons can be referenced and watched at the website http://giaoduchoanhap.edu.vn/Trang-chu.

In order to improve the quality and effectiveness of the distance learning pilot for CwD, the project board of management at MOET and CRS invites a group of national consultants to develop additional e-learning lessons for the two subjects IT and Philology grade 6 for the period from May 1st to August 31st, 2014 with the following details:

- Objective: Develop additional e-learning on IT and Philology grade 6 for the pilot model of applying IT for distance learning model of hearing and visual impairments.

- Expected outcomes: In close coordination with CRS and MOET, following outcomes are expected:

- The rest of additional lessons approximately 110 lessons for both subjects IT and philology must ensure consistency with the lessons have been developed before, in terms of contents, method and to be designed in a suitable IT technique way and meet the demand of CwD’s learning ability.

- All the e-learning lessons for visual impairement children must be demonstrated in sign language, with visual pictures and word subtitle to ensure CwD can easily learn.

- All the e-learning lessons for visual impairements must use suitable sound technique.

- Job requirements

The consultant group must have minimum of 04 consultants, in charge of each technical aspect, these include: Curriculum specialist, Specialist of special education, Specialist of e-learning lesson development, and IT specialist.

2.1 Development additional e-learning lessons for IT and philology in grade 6:

- The e-learning lessons must be developed and based on the current MOET curriculum, its approach must be followed the new curriculum after the year 2015 and to be ensure suitable with hearning and visual impairments children.

- Objective: All the lessons must be connected in terms of demonstration approach and ensure to be in consistent to the whole curriculum. Simultaniously, its contents, knowledge and skills must be simplified in contents and suitable with both visual and hearing impairement children, so that they can complete full content, knowledge, and skills for the whole school year.

- Sign language to be used in lessons, must be followed grammar/structure, and to be connected with the one which have been developed before. Questionaires, tests must be diversified for hearing impaied children with high interaction.

- Content and method for the two subjects: The content must provide adequate knowledge, skills and information must be suitable with each learner, in order to help them approach and participate in learning. Method of demonstrate the lessons must be suitable with learner’s characteristic, and be specific in guiding students and supporters, so that students can be able to participate in the e-learning in a simple and high effective way.

- Suitability: All the e-learning lessons must be developed in a way to ensure on technique, sound quality and clearly image, and to be adapted to the project.

- The total lessons that need to be developed more is 150 lessons (the consultant must balance and propose additional lessons for philology and IT)

2.2.  Development of questionnaires, tests for each lesson:

The consultant group needs to periodically develop questionnaires, exercises, tests for each e-learning, in order to revise and reconsolidate student’s knowledge, as well as evaluate results for both learners.

- Timeline: Implementation from May 2014 to the end of August 2014

| No | Job requirements | Expected outcomes (150 lessons) | Completed timeline |
| --- | --- | --- | --- |
| 1 | To develop additional lessons of IT subject for visual and hearing impairments | Complete approximately additional 45 lessons of IT subject. | 31/08/2014 |
| 2 | To develop additional lessons of Philology subject for visual and hearing impairments | Complete approximately additional 110 lessons of Philology subject. | 31/08/2014 |

(The consultant will balance the numbers of lessons according to the learner of each group based on the standard of the current general curriculum).

- Requirements for consultants:

- MA/PhD in Education;

- To have knowledge, and working experience in education, technical expertise in special education, specifically in the above two subjects;

- The consultant in charge of material development must have knowledge and experience in e-learning;

- To be expert in distance learning education and using IT to enhance education opportunity for CwD;

- Ability to connect with consultants who developed the distance learning website for CwD, the first material development consultant group, and the material approval one to be sure consistency, and completely of the two subject development.

- Applicant submission:

- Any institutions, consultants who are interested in this job should send their applications through email to Catholic Relief Services, Ms. Trần Thị Thu Hằng, at: hang.tran@crs.org; and the MOET Project Board of Management, Mr. Quach Tat Kien at: qtkien@moet.edu.vn.

- Deadline for applications: by 12h00 April 28th, 2014 (after this time all applications are not accepted).

- In the application profile, the following information should be included: Self-introduction of the consultant group’s capacity (including each consultant member’s CV), technical proposal, implementation plan and estimated budget.